## Basics
#	Organisation	Acronym	Type	Country	Personal Cost	Overheads Rate	Funding rate
1	Centre National de Recherche Scientifique	CNRS	ACA	FR		60,00%	75,00%
2	Ability Europe Limited	AEL	SME	UK	7 600,00	60,00%	75,00%
3	Consiglio Nazionale delle Ricerche	CNR	ACA	IT	4 000,00	69,90%	100,00%
4		INTHEMIS	SME	FR			75,00%
5		WIT	ACA	IR			100,00%
6	Trust-IT Services	Trust-IT	SME	UK	5 000,00	60,00%	100,00%
7
8
9
10
11
12
13
14
15
16
17

## Competencies
PLEASE PUT YOUR OWN COMPETENCIES

#	Objective/Sub-objective	Required competencies	Who (Org+person)	Comments
1	Create a trusted self-sustainable reputation-based community	Existing reputation in the field of Trust & Security
		Community management & facilitation	AEL (MM)	see www.knowledgeboard for justification
2	Set a “Quality Label”	Skills in Applied Mathematics	AEL(MM)	Dr in Applied Mathematics
		Skills in Algorithmics	AEL (MM)	Dr in Applied Mathematics
		Skills in Coding		C language, matlab, scilab, Fortran, Pascal
3	Feed the industry	Strong proved contact with Industry (Through Associations or professional organisations)

4	Feed the EC	Strong proved contact with The European Commission

5	Raise awareness	Excellent Communication Skills,	Trust-IT
		Web portal and communication tools - app development	Trust-IT

7	Derive a unique European Conference	Conference organiser with facilities and venues	Trust-IT

6	Capture hot issues	Representatives from various scientific & technical disciplines/areas	AEL (MM)	Leader of the UU4D (understanding user needs for Design) LinkedIn group within the Design Society

8	Coordinate with worldwide existing initiatives	Existing reputation in the field of Trust & Security
		Negotiation skills

## Overall Figures
Project Acronym	MACARON
Duration (Months)	36
Number of partners	7
Number of MM foreseen	180
Budget foreseen	650,000.00
Maximum Management Budget	0.07%

## Gantt
DEMINEUR			1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20
		Tâches	S-1	S-2	S-3	S-4	S-5	S-6	S-7	S-8	S-9	S-10	S-11	S-12	S-13	S-14	S-15	S-16	S-17	S-18	S-19	S-20
1	Recherches préliminaires
	T-1.1	Comprendre les règles du démineur
	T-1.2	Apprendre quelques base de Python
	T-1.3	Recherche d'une base de travail
2	Algorithmique
	T-2.1	Développement du premier algortihme
	T-2.2	Comprendre la Programmation orientée Objet
	T-2.3	Comprendre la Récurcivité
	T-2.4	Comprendre L'utilisation des interfaces graphiques
3	Programmation
	T-3.1	Développement du code
	T-3.2	Création d'une bibliothèque de test
	T-3.3	Ajout de fonctionnalitées
4	Rapport
	T-4.1	Comprendre LaTex
	T-4.2	Ecriture du rapport
	T-4.3	Comprendre comment diviser un code
	T-4.4	Ajout du code source au document LaTex

		Recherche bibliographique

		Période d'activité régulière
		Période d'activité intensive

## Events Agenda
	S-1	S-2	S-3	S-4	S-5	S-6	S-7	S-8	S-9	S-10	S-11	S-12	S-13	S-14	S-15	S-16	S-17	S-18	S-19	S-20	0	0	0	0	0	0	0	0	0	0
Consortium meetings
Advisory board meetings
Conferences
Newswires
SIG Leaders
Online Workshops
Physical workshops
ESS Seminar
EC Review

## Pers Cost
Partner Nbre	Acronym	Country	Cost model	Overhead Rates	Direct costs	Indirect costs	Total costs
1 (CO)	AEL	UK	FC	7,00%	7 200,00	504,00	7 704,00
2	CNRS	FR	FC	7,00%	6 000,00	420,00	6 420,00
3	Trust-IT	IN	FC	7,00%	5 000,00	350,00	5 350,00
4	CNR	FR	FC	7,00%	3 700,00	259,00	3 959,00
5	INT	FR	FC	7,00%	6 000,00	420,00	6 420,00

## Distribution of PMs
MACARON			1	2	3	4	5	PM	%
			UK	FR	IT	IT	FR
		Workpackages & Tasks	AEL	CNRS	Trust-IT	CNR	INT
1	Project Management		6	1	1	0	0	8	8%
	T-1.1	Comprendre les règles du démineur	3	1	1			5	63%
	T-1.2	Apprendre quelques base de Python	1					1	13%
	T-1.3	Recherche d'une base de travail	2					2	25%
		#REF !
2	Social Debate and Multi-stakeholder participation		10	7	1	6	3	27	25%
	T-2.1	Développement du premier algortihme	1	1		1	2	5	19%
	T-2.2	Comprendre la Programmation orientée Objet	4					4	15%
	T-2.3	Comprendre la Récurcivité			1	4	1	6	22%
	T-2.4	Comprendre L'utilisation des interfaces graphiques	4	2				6	22%
	T-2.5	#REF !	1	4		1		6	22%

3	Multi-discipline analysis & Reputation Management		9	13	0	6	6	34	32%
	T-3.1	Développement du code	4	4				8	24%
	T-3.2	Création d'une bibliothèque de test		2			4	6	18%
	T-3.3	Ajout de fonctionnalitées	2	3		4		9	26%
	T-3.4	#REF !	3	4		2	2	11	32%

4	Diffusion Outreach and Exploitation		6	9	12	4	6	37	35%
	T-4.1	Comprendre LaTex		2	7			9	24%
	T-4.2	Ecriture du rapport	2	3		2		7	19%
	T-4.3	Comprendre comment diviser un code	2	1	1	1		5	14%
	T-4.4	Ajout du code source au document LaTex					5	5	14%
	T-4.5	#REF !		2	3	1		6	16%
	T-4.6	#REF !	2	1	1		1	5	14%

TOTAL			31	30	14	16	15	106
0
0		MANAGEMENT	6	1	1	0	0	8	8%
0		SUPPORT	25	29	13	16	15	98	92%
0
0
0
0

## Budget Chapters
				Travel & Accomodation
				Consortium Meetings + Workshops
				Partners	Number of travels (6CM+7Conf)	Travel cost	Accomodation Cost (CM+7 Conferences)	Nbre of days	Total Travel	Total Accomodation	Total
				AEL	6	300,00	245,00	24,000000000000000	1 800,00	5 880,00	7 680,00
				CNRS	6	300,00	245,00	24,000000000000000	1 800,00	5 880,00	7 680,00
				Trust-IT	6	300,00	245,00	24,000000000000000	1 800,00	5 880,00	7 680,00
				CNR	6	300,00	245,00	24,000000000000000	1 800,00	5 880,00	7 680,00
				INT	6	300,00	245,00	24,000000000000000	1 800,00	5 880,00	7 680,00

Dissemination, Web Channel, App									TOTAL	38 400,00
Dissemination Material		8 500,00
MACARON Web Channel		15 000,00
MACARON APP		5 000,00
				Coordination with the Project Officier
				Partners	Number of travels	Travel cost	Accomodation Cost	Nbre of days	Total Travel	Total Accomodation	Total
				AEL	6	100,00	245,00	6,000000000000000	600,00	1 470,00	2 070,00
TOTAL		28 500,00

				Advisory Group and SIG leaders meeting & conferences
TOTAL OTHERS		175110		Number of SIGs	Number of travels (3 meetings + 7 conferences & workshops)	Travel cost	Accomodation Cost	Nbre of days	Total Travel	Total Accomodation	Total
				8	4	300,00	245,00	2,000000000000000	9 600,00	15 680,00	25 280,00
Costs for workshops
	Year 1	Year 2	Year 3
Number of workshops	1	2	1
Room Renting	1 000,00	1 000,00	1 000,00	4 000,00
Audio tools	2 000,00	2 000,00	2 000,00	8 000,00
Catering	1 500,00	1 500,00	1 500,00	6 000,00
Publicising	1 000,00	1 000,00	1 000,00	4 000,00
		TOTAL		22 000,00

				Conferences
	Total Other Cost			Number of Conferences	Number of travels	Travel cost	Accomodation Cost	Nbre of days	Total Travel	Total Accomodation	Total
AEL	54 650,00		AEL	6	6	300,00	245,00	18,000000000000000	10 800,00	8 820,00	19 620,00
CNRS	27 300,00		CNRS	6	6	300,00	245,00	18,000000000000000	10 800,00	8 820,00	19 620,00
Trust-IT	58 180,00		Trust-IT			300,00		0,000000000000000	0,00	0,00	0,00
CNR	27 300,00		CNR	6	6	300,00	245,00	18,000000000000000	10 800,00	8 820,00	19 620,00
INT	7 680,00		INT			300,00		0,000000000000000	0,00	0,00	0,00
	175 110,00
									58 860,00

			CNR	KO	CM	WS	Review	SG	Total
			M1	1	2				3
			M6		2			1	3
			M12		2	1	1	1	5
			M18		2	1		1	4
			M24		2	1		1	4
			M30		2	1	1	1	5
				1	12	4	2	5	24

OTHER COSTS
Travel & Acomodation	40470
Advisory group	25280
Conferences & Workshops	80860
Media Channels	28500
Total	175110

## Table 1.3a
Work package No	Work package title	Type of activity	Lead partic no.	Lead partic. short name	Person-months	Start month	End month
1	Recherches préliminaires	MGT	1	AEL	8	1	36
2	Algorithmique	SUPP		AEL	27	1	36
3	Programmation	SUPP	3	CNRS	34	1	36
4	Rapport	SUPP	2	Trust-IT	37	1	36
	TOTAL				106

## Table1.3e
Partic. no.	Partic. short name	WP-1	WP-2	WP-3	WP-4	Total PM
1	AEL	6	10	9	6	31
2	CNRS	1	7	13	9	30
3	Trust-IT	1	1	0	12	14
4	CNR	0	6	6	4	16
5	INT	0	3	6	6	15
TOTAL		8	27	34	37	106

## Deliverables
Del. no.	Deliverable name	WP n°	Nature	Dissemination Level	Delivery Date
D-1.1	Consortium agreement	1	R	C	M-4
D-1.2	First interim report on activities	1	R	PU	M-6
D-1.3	Yearly report on activities	1	R	C	M-12
D-1.4	Second interim report	1	R	PU	M-18
D-1.5	Second yearly report on activities	1	R	C	M-24
D-1.6	Third interim report	1	R	PU	M-30
D-1.7	Final report on activities	1	R	C	M-36

D-2.1
D-2.2
D-2.3
D-2.4
D-2.2
D-2.3
D-2.4
D-2.5
D-2.6
D-2.7

## Milestones
Milestone Number	Date	Description
MS-1
MS-2
MS-3
MS-4
MS-5

## Table 1
Activity Type

Research activities
WP-2
WP-3
WP-4
WP-5
WP-6
Total

Management activities
WP-1
Total

Other activities

Total

Total Beneficiaries

## Table 2
Estimated eligible costs (whole duration of the project)
					MGT		SUPP			OTH
#	Partners	Personal Cost		MGT	SUPP	RTD	OTH	Method of calc. indirect costs	Costs	Req. EC funding	Costs	SUPP Funding rate	Req. EC funding	Costs	Req. EC funding	Eligible Costs	Receipts	Req. EC funding
1	AEL	7 704,00		6	25	0	0	FC	46 224,00	46 224,00	192 600,00	100,00%	192 600,00	54 650,00	54 650,00	293 474,00	0,00	293 474,00
2	CNRS	6 420,00		1	29	0	0	FC	6 420,00	6 420,00	186 180,00	100,00%	186 180,00	27 300,00	27 300,00	219 900,00	0,00	219 900,00
3	Trust-IT	5 350,00		1	13	0	0	FC	5 350,00	5 350,00	69 550,00	100,00%	69 550,00	58 180,00	58 180,00	133 080,00	0,00	133 080,00
4	CNR	3 959,00		0	16	0	0	FC	0,00	0,00	63 344,00	100,00%	63 344,00	27 300,00	27 300,00	90 644,00	0,00	90 644,00
5	INT	6 420,00		0	15	0	0	FC	0,00	0,00	96 300,00	100,00%	96 300,00	7 680,00	7 680,00	103 980,00	0,00	103 980,00
				8	98	0	0		57 994,00	57 994,00	607 974,00		607 974,00	175 110,00	175 110,00	841 078,00	0,00	841 078,00

					check	5,50%				check	0,00		max	800 000,00
					MANAGEMENT					OTHER COSTS			GLOBAL
					Status	OK				Status	OK		Status	OVER LIMIT

	DATA				SUPP				MGT				OTH				TOTAL
		personal costs	SUPP	MGT	Cost	Indirect	Total	Requested	Cost	Indirect	Total	Requested	Cost	Indirect	Total	Requested
	AEL	7200	25	6	180000	12600	192600	192600	43200	3024	46224	46224	54650	3825,5	58475,5	58475,5	297299,5
	CNRS	6000	29	1	174000	12180	186180	186180	6000	420	6420	6420	27300	1911	29211	29211	221811
	Trust-IT	5000	13	1	65000	4550	69550	69550	5000	350	5350	5350	58180	4072,6	62252,6	62252,6	137152,6
	CNR	3700	16	0	59200	4144	63344	63344	0	0	0	0	27300	1911	29211	29211	92555
	INT	6000	15	0	90000	6300	96300	96300	0	0	0	0	7680	537,6	8217,6	8217,6	104517,6
					568200	39774	607974	607974	54200	3794	57994	57994	175110	12257,7	187367,7	187367,7	853335,7
					71,25%				6,80%				21,96%	71,25%

					AEL				CNRS
					SUPP	MGT	Total		SUPP	MGT	Total
					PC	180000	43200	223200	PC	174000	6000	180000
					OTH	54650		54650	OTH	27300		27300
					Ind	16425,5	3024	19449,5	Ind	14091	420	14511
					Total	251075,5	46224	297299,5	Total	215391	6420	221811
					Req	251075,5	46224	297299,5	Req	215391	6420	221811
					Labor			622400
					TRUST-IT				CNR					Travel			65750
					SUPP	MGT	Total		SUPP	MGT	Total			Equipment
					PC	65000	5000	70000	PC	59200	0	59200			Consumables
					OTH	58180		58180	OTH	27300		27300			IPR protection
					Ind	8622,6	350	8972,6	Ind	6055	0	6055			Other (Workshops & Conferences)			109360
					Total	131802,6	5350	137152,6	Total	92555	0	92555			Indirect costs			55825,7
					Req	131802,6	5350	137152,6	Req	92555	0	92555			Audits
					Subcontracting
					INT					Total budget			853335,7
					SUPP	MGT	Total					²
					PC	90000	0	90000
					OTH	7680		7680
					Ind	6837,6	0	6837,6
					Total	104517,6	0	104517,6
					Req	104517,6	0	104517,6

## Table 3
	P1	P2	P3	P4	P5	P6	P7
TRAVEL & ACCOMODATION
CONFERENCES
FURNITURES & CONSUMABLES
ADVISORY BOARD
LICENCING
AUDITING
SUBCONTRACTING
RTD
MGT
OTH
Overhead rates
Funding rates
Personal costs

Detailed resources
Activity Type

Research activities
Staff Effort
Personnel Costs (€)
Subcontracting (€)
Other Costs (€)
Indirect Costs (€) (Real indirect)
Total Costs (€)
Reimbursement Rate
EC Contribution (€)

Demonstration activities
Staff Effort
Personnel Costs (€)
Subcontracting (€)
Other Costs (€)
Indirect Costs (€) (Real indirect)
Total Costs (€)
Reimbursement Rate
EC Contribution (€)

Management activities
Staff Effort
Personnel Costs (€)
Subcontracting (€)
Other Costs (€)
Indirect Costs (€) (Real indirect)
Total Costs (€)
Reimbursement Rate
EC Contribution (€)

Other activities
Staff Effort
Personnel Costs (€)
Subcontracting (€)
Other Costs (€)
Indirect Costs (€) (Real indirect)
Total Costs (€)
Reimbursement Rate
EC Contribution (€)

Project Total Costs (€)
Project EC Contribution (€)

## Sheet17
	Number of working days per event.
	Kick-Off meeting	Consortium metings	Workshops	Project review	SIG Leaders meetings	Total
M1	1	2				3
M6		2			1	3
M12		2	1	1	1	5
M18		2	1		1	4
M24		2	1		1	4
M30		2	1	1	1	5
	1	12	4	2	5	24